The ACM Group
CoNetPad

---
Presentation Overview
Project Management
Project Description
Motivation
Use Cases
Project Plan
Risk Management

---
CoNetPad
Collaborative
Network-based
Editing tool/Pad

---
Project Management
The ACM Group consists of Josh Tan, Justin Anderson and Cesar Ramirez
decentralized team structure
use Git as configuration management tool
repository update policy will require that each member commit their work at least twice a week

---
Project Description
Goal
Provide simple, real-time collaboration for small software projects
Audience
Small teams
Educators (mentor-mentee environment)

---
Motivation
Existing collaboration tools often fail to offer real-time collaboration.
Those that do tend to require a long deployment process or are non-free services.

---
Use Cases
Programming and AI competitions:
Usually single file with complex content.
Collaboration is important but usually hindered by the lack of quick source code sharing.

---
Use Cases
Educational tool:
Kids can collaborate in simple programming projects.
Instructors can provide real-time feedback within the editor itself.

---
Project Plan
Work Breakdown Diagram:
Four main phases
Requirements analysis
Design (system and program)
Code implementation
Testing

---
Project Plan
Activity Graph:
Implementation of client and server can be done in parallel
Estimated the number of days each activity would require
  - Server Code > Client Code

---
Project Plan
PERT Chart:
Gantt Chart:
Critical path shown in red
Shortest possible time = 62 (business) days
5 days slack for client implementation and testing

---
Risk Management
Two main components
  - Server
  - Client
Requirements
  - Components interact asynchronously
  - Offer a seamless experience
Five major risks
Sockets and networking
Database concurrency and data integrity
Highlighting and auto-complete
Latency problems with network
Time constraints

---
Errors related to sockets and network
Number of connections and sockets can cause unexpected problems
Adverse conditions
  - low bandwidth
  - high latency
  - temporary disconnections
Develop testing tool for automated testing
If network architecture does not work appropriately, we will simplify it
All of our members have worked with sockets and networking, so the probability of this risk is relatively low

---
Problems with database concurrency and data integrity
Multiple sources editing a single file is a common source of concurrency problems and data loss.
Queue-based program design that will prevent the problem of multiple writes to a file.
A prototype will be developed early on in our development cycle.
In the case of inherent problems with our design we will move to traditional approach(using a database lock).

---
Difficulties with highlighting and auto-complete
Highlighting and auto-complete are two important features.
But the implementation for these features is still unclear for the team.
The process of implementing this feature will be decided early on in the design process.
If the implementation is too costly then this features wont be included.

---
Latency problems with network
Real-time collaboration requires low latency.
Client and server will be tested under different circumstances, making sure that each message takes less than 1.5 seconds.
This testing will be done periodically and after any significant change.
If latency problems arise, we may modify the frequency and/or size of the data exchanged.

---
Time constraints or personal circumstances
There is always the possibility that personal circumstances may occur.
All the team members are active members of the Association for Computing Machinery.
We can combat this risk using strict schedules and by continuously checking our progress.
If we fail to progress at the expected rate, we will limit our feature set but always emphasizing the best user experience.